## Summary
AGILE PROGRESS REPORT — 18 JUN 2026
Period: 18 Jun 2026 – 18 Jun 2026 ¦ Prepared by: Thiravidam S
KPI SNAPSHOT
Issues Opened | Issues Resolved | Reqs Opened | Reqs Closed | Open Support | At-Risk Items
10 | 13 | 13 | 147 | 0 | 98
TEAM DELIVERY SUMMARY
Owner | Items Delivered | Bugs Fixed | Reqs Done | Tests Fixed | Modules
Thiravidam | 10 | 9 | 0 | 0 | Sales & Distribution, Admin
Gowtham | 13 | 0 | 13 | 0 | Sales Invoice PDF, Dispatch Order
Dhanalakshmi | 16 | 1 | 0 | 15 | HR Shift Roster, Calendar, Reports
RISK: HR Overtime module blocked — all API endpoints returning 500 errors (HR-OT-001). Escalation required.

## Issues
ISSUES — 18 Jun 2026 (10 Raised ¦ 13 Resolved)
ID | Owner | Reported By | Description | Severity | Status | Open Date
#1 | Dhanalakshmi | Dhanalakshmi | HR Overtime > New OT Entry — column sa.effective_date does not exist | MEDIUM | Closed | 2026-06-18
#2 | Thiravidam | Mr. Ragesh | Sales > Sales Orders > Credit Summary — Available Credit field reordered to appear after Credit Limit and before Invoice Outstanding | LOW | Fixed | 2026-06-18
#3 | Thiravidam | Thiravidam | Sales > Price Approvals — raw i18n keys showing (approvals.json not registered in i18n/request.ts namespace list) | HIGH | Fixed | 2026-06-18
#4 | Thiravidam | Thiravidam | Sales > Price Approvals — page heading shows 'Title' instead of 'Price Approvals' (duplicate title key in approvals.json) | MEDIUM | Fixed | 2026-06-18
#5 | Thiravidam | Manjunath | Sales > Sales Orders > Pending Approvals — title, table & column headings coming from backend | HIGH | Fixed | 2026-06-18
#6 | Thiravidam | Manjunath | Sales > Sales Orders > Approval History — title, table & column headings coming from backend | HIGH | Fixed | 2026-06-18
#7 | Thiravidam | Thiravidam | Admin > Monitoring — JS crash: activityData.map is not a function (double-wrapped service response envelope) | HIGH | Fixed | 2026-06-18
#8 | Thiravidam | Thiravidam | Admin > Monitoring — missing i18n keys for statusIndicators, activityFilters, metrics, detailedMetrics in admin.json | MEDIUM | Fixed | 2026-06-18
#9 | Thiravidam | Thiravidam | Admin > Users/Roles/Settings/Audit/Security/Feature Toggles — raw i18n keys (rbac.json, monitoring.json, notifications.json, shifts.json not registered) | HIGH | Fixed | 2026-06-18
#10 | Thiravidam | Thiravidam | Admin > Sidebar — DGFT/IEC nav item fires MISSING_MESSAGE error (dgftIec key missing from navigation.json locales) | LOW | Fixed | 2026-06-18

## Requirements
REQUIREMENTS — 18 Jun 2026 (13 Opened ¦ 13 Done)
Req ID | Module | Description | Requestor | Priority | Status | Owner
SAL-045 | Sales / Invoice PDF | Add Reels column to invoice PDF line items table | Mr. Ragesh | MEDIUM | Done | Gowtham
SAL-046 | Sales / Invoice PDF | Add Bundles column to invoice PDF line items table | Mr. Ragesh | MEDIUM | Done | Gowtham
SAL-047 | Sales / Invoice PDF | Remove Place of Supply field from invoice PDF header | Mr. Ragesh | LOW | Done | Gowtham
SAL-048 | Sales / Invoice PDF | Remove Financial Year (26-27) field from invoice PDF header | Mr. Ragesh | LOW | Done | Gowtham
SAL-049 | Sales / Invoice PDF | Remove A/C Type field from bank details section in invoice PDF | Mr. Ragesh | LOW | Done | Gowtham
SAL-050 | Sales / Invoice PDF | Fix discount display — use totalDiscount not headerDiscountAmount | Mr. Ragesh | HIGH | Done | Gowtham
SAL-051 | Sales / Invoice PDF | Fix IGST calculation denominator — use taxableAmount not grand total | Mr. Ragesh | HIGH | Done | Gowtham
SAL-052 | Sales / Invoice PDF | Fix invoice summary row order — Discount row before Freight row | Mr. Ragesh | MEDIUM | Done | Gowtham
SAL-053 | Sales / Invoice API | Embed bank account data in invoice API response via LEFT JOIN finance.bank_accounts | Mr. Ragesh | HIGH | Done | Gowtham
DPO-012 | Dispatch / Weight Calc | Fix dispatch weight double-counting — correct COALESCE source hierarchy | Mr. Ragesh | HIGH | Done | Gowtham
DPO-013 | Dispatch / Batch Assign | Add fg_entry_allocations fallback in suggestBatches for FG batches without stock ledger | Mr. Ragesh | HIGH | Done | Gowtham
DPO-014 | Dispatch / Loading Plan | Fix bundle count data flow from dispatch order to invoice PDF (bundleNumbers) | Mr. Ragesh | MEDIUM | Done | Gowtham
DPO-015 | Dispatch / Loading Plan | Fix batch dropdown ordering — show DESC (most recent batch first) | Mr. Ragesh | MEDIUM | Done | Gowtham

## Test Items
TEST ITEMS — 18 Jun 2026 (34 Active)
Test ID | Module | Sub Module | Description | Owner | Priority | Status
TEST-SD-028 | Sales & Distribution | — | Pending investigation | Admin | MEDIUM | Open
HR-OT-001 | HR > Overtime | Overtime | BLOCKING: All API endpoints returning 500 errors on page load | Admin | MEDIUM | Open
HR-OT-002 | HR > Overtime | Overtime | Validation Error | Admin | MEDIUM | Open
HR-OT-003 | HR > Overtime | Overtime | UI/UX issues | Admin | MEDIUM | Open
TEST-SD-031 | Sales & Distribution | Sales > Orders > Create Form > Order Header Step | Order header step test | Thiravidam | LOW | Closed
TEST-SD-032 | Sales & Distribution | Sales > Orders > Create Form > Billing Address | Billing address test | Thiravidam | MEDIUM | Closed
TEST-SD-033 | Sales & Distribution | Dispatch Order | Dispatch order test | Gowtham | MEDIUM | Closed
TEST-SD-034 | Sales & Distribution | Dispatch Order | Dispatch order high priority test | Gowtham | HIGH | Closed
TEST-SD-035 | Sales & Distribution | Sales > Sales Orders > Print / PDF > Bill To Party Bank Details | Bank Details Card test | Thiravidam | HIGH | Closed
TEST-SD-036 | Sales & Distribution | Sales > Sales Orders > Print / PDF > Bank Details Fix | Bank Details Not Showing Fix | Thiravidam | HIGH | Closed
TEST-SD-037 | Sales & Distribution | Sales Order > Pending Approvals | Pending Approvals test | Thiravidam | HIGH | Closed
TEST-SD-038 | Sales & Distribution | Sales Order > Approvals History | Approvals History test | Thiravidam | HIGH | Closed
TEST-SD-039 | Sales & Distribution | Sales > Sales Orders > Print / PDF > Export Order | Amount in Words showing as formatted number instead of words | Thiravidam | MEDIUM | Closed
TEST-SD-040 | Sales & Distribution | Sales > Orders > Items Tab | Items Tab test | Gowtham | MEDIUM | Closed
TEST-001 | Sales & Distribution | Sales > Orders > Backend Schema | Backend Schema test | Gowtham | HIGH | Fixed
TEST-002 | Sales & Distribution | Sales > Orders > Order Header Step | Order Header Step test | Gowtham | HIGH | Fixed
TEST-003 | Sales & Distribution | Sales > Invoice | Invoice test | Gowtham | MEDIUM | Fixed
TEST-004 | Sales & Distribution | Parties > Address Management | Address Management test | Gowtham | MEDIUM | Fixed
TEST-005 | Sales & Distribution | Parties > Address Dialog | Address Dialog test | Gowtham | MEDIUM | Fixed
HR-SH-TEST-001 | HR > Shift Roster | Shift Roster — Matrix View | Chaotic/non-deterministic shift matrix pattern | Dhanalakshmi | MEDIUM | Fixed
HR-SH-TEST-002 | HR > Shift Roster | Shift Roster — Matrix View | Weekly off day not displayed in matrix | Dhanalakshmi | MEDIUM | Fixed
HR-SH-TEST-003 | HR > Shift Roster | Shift Roster — Matrix View | ABC/BCA/CAB rotation broken | Dhanalakshmi | MEDIUM | Fixed
HR-SH-TEST-004 | HR > Shift Roster | Shift Roster — Matrix View | Shift Group dropdown removed from template apply popup | Dhanalakshmi | MEDIUM | Fixed
HR-SH-TEST-005 | HR > Shift Roster | Shift Roster — Matrix View | Shifts dropdown empty in roster templates | Dhanalakshmi | MEDIUM | Fixed
HR-SH-TEST-006 | HR > Shift Roster | Shift Roster — Matrix View | Night shift pre-seed window too short | Dhanalakshmi | MEDIUM | Fixed
HR-SH-TEST-007 | HR > Shift Roster | Shift Roster — Matrix View | is_night_shift column missing on /hr/shifts/master | Dhanalakshmi | MEDIUM | Fixed
HR-SH-TEST-008 | HR > Shift Calendar | Shift Calendar | Calendar shows no data | Dhanalakshmi | MEDIUM | Fixed
HR-SH-TEST-009 | HR > Shift Calendar | Shift Calendar | Shift legend showing wrong shifts | Dhanalakshmi | MEDIUM | Fixed
HR-SH-TEST-010 | HR > Shift Reports | Shift Reports | All report queries referencing wrong schema | Dhanalakshmi | MEDIUM | Fixed
HR-SH-TEST-011 | HR > Shift Reports | Shift Reports | Employee Assignment History tab showing empty | Dhanalakshmi | MEDIUM | Fixed
HR-SH-TEST-012 | HR > Shift Reports | Shift Reports | Employee history returning thousands of inactive records | Dhanalakshmi | MEDIUM | Fixed
HR-SH-TEST-013 | HR > Shift Reports | Shift Reports | Duplicate assignment report showing false positives | Dhanalakshmi | MEDIUM | Fixed
HR-SH-TEST-014 | HR > Shift Reports | Shift Reports | Night shift compliance report returning zero results | Dhanalakshmi | MEDIUM | Fixed
HR-SH-TEST-015 | HR > Shift Reports | Shift Reports | Shift filter dropdown in reports using production shifts | Dhanalakshmi | MEDIUM | Fixed

## Support
SUPPORT TICKETS — 18 Jun 2026 (1 Ticket ¦ All Closed)
Customer | Product | Requirement | Requestor | Priority | Status | Owner
Netique | BPApp | PriceList Documentation | Ananda Ravi | HIGH | Completed | Thiravidam