## Team Summary
PapyrusBP — Weekly Progress Report 08-Jun-2026 to 13-Jun-2026
Branch: netique_team_v2 ¦ Sprint 2 ¦ Team Total: 168 commits this week
DEVELOPER COMMIT TOTALS THIS WEEK
| Developer | Total | feat | fix | refactor | test | chore | merge
| Thiravidam | 57 | 9 | 35 | 0 | 0 | 2 | 11
| Gowtham | 72 | 29 | 36 | 2 | 1 | 0 | 0
| Dhanalakshmi | 39 | 8 | 22 | 0 | 0 | 3 | 5
MODULE BREAKDOWN BY DEVELOPER
| Developer | Module | feat | fix | refactor | test | other | Total
| Thiravidam | BOM | 1 | 1 | 0 | 0 | 0 | 2
| Thiravidam | BOM-CALCULATION | 0 | 1 | 0 | 0 | 0 | 1
| Thiravidam | E2E | 0 | 1 | 0 | 0 | 0 | 1
| Thiravidam | GENERAL | 0 | 0 | 0 | 0 | 11 | 11
| Thiravidam | INVENTORY | 0 | 2 | 0 | 0 | 0 | 2
| Thiravidam | MERGE | 0 | 0 | 0 | 0 | 1 | 1
| Thiravidam | MIGRATIONS | 0 | 1 | 0 | 0 | 1 | 2
| Thiravidam | NAV | 1 | 0 | 0 | 0 | 0 | 1
| Thiravidam | PARTIES | 0 | 2 | 0 | 0 | 0 | 2
| Thiravidam | PROCUREMENT | 0 | 10 | 0 | 0 | 0 | 10
| Thiravidam | PRODUCTION | 2 | 2 | 0 | 0 | 0 | 4
| Thiravidam | SALES | 5 | 14 | 0 | 0 | 0 | 19
| Thiravidam | VENDOR-INVOICES | 0 | 1 | 0 | 0 | 0 | 1
| Gowtham | DISPATCH | 2 | 7 | 0 | 0 | 0 | 9
| Gowtham | DISPATCH-ORDERS | 1 | 0 | 0 | 0 | 0 | 1
| Gowtham | E2E | 0 | 0 | 0 | 1 | 0 | 1
| Gowtham | GENERAL | 0 | 0 | 0 | 0 | 2 | 2
| Gowtham | HR | 0 | 1 | 0 | 0 | 0 | 1
| Gowtham | INVOICES | 4 | 2 | 0 | 0 | 0 | 6
| Gowtham | ORGANIZATION | 1 | 0 | 0 | 0 | 0 | 1
| Gowtham | PARTIES | 0 | 3 | 0 | 0 | 0 | 3
| Gowtham | PRICE-CIRCULAR | 2 | 1 | 0 | 0 | 0 | 3
| Gowtham | PRODUCT-CATALOG | 1 | 2 | 0 | 0 | 0 | 3
| Gowtham | SALES | 13 | 19 | 0 | 0 | 1 | 33
| Gowtham | SALES-ORDERS | 5 | 1 | 2 | 0 | 0 | 8
| Gowtham | SPECS | 0 | 0 | 0 | 0 | 1 | 1
| Dhanalakshmi | ESS | 3 | 3 | 0 | 0 | 0 | 6
| Dhanalakshmi | GENERAL | 0 | 0 | 0 | 0 | 6 | 6
| Dhanalakshmi | HR | 5 | 10 | 0 | 0 | 0 | 15
| Dhanalakshmi | HR/OVERTIME | 0 | 1 | 0 | 0 | 0 | 1
| Dhanalakshmi | I18N | 0 | 1 | 0 | 0 | 0 | 1
| Dhanalakshmi | LICENSING | 0 | 2 | 0 | 0 | 0 | 2
| Dhanalakshmi | MIGRATIONS | 0 | 0 | 0 | 0 | 1 | 1
| Dhanalakshmi | OVERTIME | 0 | 4 | 0 | 0 | 0 | 4
| Dhanalakshmi | SEEDS | 0 | 0 | 0 | 0 | 2 | 2
| Dhanalakshmi | SEPARATION | 0 | 1 | 0 | 0 | 0 | 1

## Thiravidam
Weekly Report — Thiravidam ¦ 08-Jun-2026 to 13-Jun-2026
Branch: netique_team_v2 ¦ Sprint 2
MY WEEK IN NUMBERS
| 57 | 9 | 35 | 2 | 13
| Total Commits | New Features | Bug Fixes | Other | Modules
MODULES WORKED ON
| Module | feat | fix | other | Total
| BOM | 1 | 1 | 0 | 2
| BOM-CALCULATION | 0 | 1 | 0 | 1
| E2E | 0 | 1 | 0 | 1
| GENERAL | 0 | 0 | 11 | 11
| INVENTORY | 0 | 2 | 0 | 2
| MERGE | 0 | 0 | 1 | 1
| MIGRATIONS | 0 | 1 | 1 | 2
| NAV | 1 | 0 | 0 | 1
| PARTIES | 0 | 2 | 0 | 2
| PROCUREMENT | 0 | 10 | 0 | 10
| PRODUCTION | 2 | 2 | 0 | 4
| SALES | 5 | 14 | 0 | 19
| VENDOR-INVOICES | 0 | 1 | 0 | 1
13-Jun-2026 (Saturday) — 7 commits (3 feat ¦ 4 fix ¦ 0 other)
| Hash | Type | Module | Commit Message | Date
| 13a359032 | FEAT | SALES | feat(sales): add per-row print button to sales order list | 2026-06-13
| 017e823b4 | FEAT | SALES | feat(sales): add always-visible Print Report button to sales order list | 2026-06-13
| b0b164838 | FEAT | SALES | feat(sales): display bill-to customer as code - name in order form | 2026-06-13
| 19acc7502 | FIX | SALES | fix(sales): enable round off by default on new sales orders | 2026-06-13
| 517d10cff | FIX | SALES | fix(sales): filter bill-to customer list by order type | 2026-06-13
| efcfe238f | FIX | SALES | fix(sales): restrict product search to finished goods only in sales orders | 2026-06-13
| c286901e4 | FIX | SALES | fix(sales): show newly created products immediately in order form search | 2026-06-13
12-Jun-2026 (Friday) — 16 commits (2 feat ¦ 11 fix ¦ 3 other)
| Hash | Type | Module | Commit Message | Date
| 259e6e495 | FEAT | SALES | feat(sales): show per-adjustment discount breakdown in line items | 2026-06-12
| 289a4f533 | FEAT | SALES | feat(sales): add discount remarks section to sales order form | 2026-06-12
| a8a75080c | FIX | SALES | fix(sales): prioritize form-specific price rules over any-form rules | 2026-06-12
| b64b0ed08 | FIX | SALES | fix(sales): filter billing address dropdown to BILLING and REGISTERED types only | 2026-06-12
| a7e1f71e6 | FIX | SALES | fix(sales): move Reverse Charge after PO Date; hide Addresses card | 2026-06-12
| 2ed2297b6 | FIX | SALES | fix(sales): move Partner Details section after Ship-to, before Payment Terms | 2026-06-12
| 0aada93be | FIX | SALES | fix(sales): hide GST/Tax, Buyer GSTIN, Place of Supply in address tab | 2026-06-12
| ee1aa1d1c | FIX | SALES | fix(sales): add GST number to shipping address display | 2026-06-12
| d436541aa | FIX | SALES | fix(sales): show state name not code; add GST after billing address | 2026-06-12
| ae2623ec1 | FIX | SALES | fix(sales): resolve numeric state code to state name in address display | 2026-06-12
| 7c2941e7b | FIX | SALES | fix(sales): show state name instead of numeric GST code in billing/shipping address | 2026-06-12
| 5e0ab985f | FIX | SALES | fix(sales): resolve state code to state name in billing/shipping address display | 2026-06-12
| 7e56ec312 | FIX | PROCUREMENT | fix(procurement): fix dark mode visibility on quotation comparison page | 2026-06-12
| 7a51b66eb | CHORE | MERGE | chore(merge): resolve LineItemsStepForm conflict | 2026-06-12
| b5682935b | MERGE | GENERAL | Merge branch 'netique_team_v2' | 2026-06-12
| 98dadad22 | MERGE | GENERAL | Merge branch 'netique_team_v2' | 2026-06-12
11-Jun-2026 (Thursday) — 20 commits (0 feat ¦ 15 fix ¦ 5 other)
| Hash | Type | Module | Commit Message | Date
| 2dcbdd17f | FIX | PROCUREMENT | fix(procurement): include per-line discounts in quotation header totals | 2026-06-11
| d241c3af9 | FIX | PROCUREMENT | fix(procurement): recalculate import quotation landed costs (CF/LT per-unit) | 2026-06-11
| 31b5cf9c7 | FIX | INVENTORY | fix(inventory): sync MR line issued_qty when material issue is approved | 2026-06-11
| df13d01c0 | FIX | PRODUCTION | fix(production): fix MR Post Goods Issue showing zero in Lines tab | 2026-06-11
| e159722eb | FIX | PRODUCTION | fix(production): sync MR line issued_quantity when material issued via WO | 2026-06-11
| a8ab87902 | FIX | PROCUREMENT | fix(procurement): fix totalTaxAmount mapping reading non-existent field | 2026-06-11
| 684fd432f | FIX | PROCUREMENT | fix(procurement): fix tax rate always showing 0 in PO view/edit | 2026-06-11
| a1b670998 | FIX | PROCUREMENT | fix(procurement): show landed cost INR for import quotations in list | 2026-06-11
| 0cb4ffb75 | FIX | PROCUREMENT | fix(procurement): migration to recalculate stale quotation header totals | 2026-06-11
| e63587c12 | FIX | PROCUREMENT | fix(procurement): fix PO list page showing 0 for total amount | 2026-06-11
| 34e2ad091 | FIX | PARTIES | fix(parties): align certification type and status values with DB constraints | 2026-06-11
| 5656c32be | FIX | PARTIES | fix(parties): align certification status values with backend validator | 2026-06-11
| fd5f50fdc | FIX | PROCUREMENT | fix(procurement): include tax in PR estimated amount and review total | 2026-06-11
| dce8f90d2 | FIX | PROCUREMENT | fix(procurement): sync quotation header totals when lines are updated | 2026-06-11
| 366d38611 | FIX | MIGRATIONS | fix(migrations): restore 8 tampered reporting migrations + guard V7.96 GR/IR insert | 2026-06-11
| f18d1d8fb | MERGE | GENERAL | Merge branch 'netique_team_v2' | 2026-06-11
| bd4b9948a | MERGE | GENERAL | Merge branch 'netique_team_v2' | 2026-06-11
| 8591cc246 | MERGE | GENERAL | Merge branch 'netique_team_v2' | 2026-06-11
| 242e766d6 | MERGE | GENERAL | Merge branch 'netique_team_v2' | 2026-06-11
| 1296cdd90 | MERGE | GENERAL | Merge branch 'netique_team_v2' | 2026-06-11
10-Jun-2026 (Wednesday) — 2 commits (0 feat ¦ 1 fix ¦ 1 other)
| Hash | Type | Module | Commit Message | Date
| 23625339e | FIX | E2E | fix(e2e): correct import paths in advance-payment test + refresh health stats | 2026-06-10
| 249e362dd | MERGE | GENERAL | Merge branch 'netique_team_v2' | 2026-06-10
09-Jun-2026 (Tuesday) — 2 commits (1 feat ¦ 1 fix ¦ 0 other)
| Hash | Type | Module | Commit Message | Date
| f3814b442 | FEAT | NAV | feat(nav): move GRN Dashboard & Reports from procurement to inventory | 2026-06-09
| c7835636a | FIX | VENDOR-INVOICES | fix(vendor-invoices): fix empty page and add create invoice dialog | 2026-06-09
08-Jun-2026 (Monday) — 10 commits (3 feat ¦ 3 fix ¦ 4 other)
| Hash | Type | Module | Commit Message | Date
| 0549c4630 | FEAT | PRODUCTION | feat(production): add cancel and delete actions to material requisitions list | 2026-06-08
| 69e1b1f64 | FEAT | PRODUCTION | feat(production): add BOM Calculation page and fix material requisitions | 2026-06-08
| 6c64353e2 | FEAT | BOM | feat(bom): separate raw/chemical/fuel product dropdowns by category | 2026-06-08
| 07692a834 | FIX | BOM-CALCULATION | fix(bom-calculation): show only active BOM templates in product dropdown | 2026-06-08
| 6e0b775dc | FIX | BOM | fix(bom): auto-fill fuel UOM from product primary_uom_id on row add | 2026-06-08
| 90b0d48a1 | FIX | INVENTORY | fix(inventory): remove duplicate NcrActionType export in api-client index | 2026-06-08
| 0daaac799 | CHORE | MIGRATIONS | chore(migrations): restore missing files to unblock migrate runner | 2026-06-08
| 300722081 | MERGE | GENERAL | Merge branch 'netique_team_v2' | 2026-06-08
| 104bef99a | MERGE | GENERAL | Merge branch 'netique_team_v2' | 2026-06-08
| bf8cda360 | MERGE | GENERAL | Merge branch 'netique_team_v2' | 2026-06-08

## Gowtham
Weekly Report — Gowtham ¦ 08-Jun-2026 to 13-Jun-2026
Branch: netique_team_v2 ¦ Sprint 2
MY WEEK IN NUMBERS
| 72 | 29 | 36 | 3 | 13
| Total Commits | New Features | Bug Fixes | Other | Modules
MODULES WORKED ON
| Module | feat | fix | other | Total
| DISPATCH | 2 | 7 | 0 | 9
| DISPATCH-ORDERS | 1 | 0 | 0 | 1
| E2E | 0 | 0 | 1 | 1
| GENERAL | 0 | 0 | 2 | 2
| HR | 0 | 1 | 0 | 1
| INVOICES | 4 | 2 | 0 | 6
| ORGANIZATION | 1 | 0 | 0 | 1
| PARTIES | 0 | 3 | 0 | 3
| PRICE-CIRCULAR | 2 | 1 | 0 | 3
| PRODUCT-CATALOG | 1 | 2 | 0 | 3
| SALES | 13 | 19 | 1 | 33
| SALES-ORDERS | 5 | 1 | 2 | 8
| SPECS | 0 | 0 | 1 | 1
13-Jun-2026 (Saturday) — 6 commits (3 feat ¦ 3 fix ¦ 0 other)
| Hash | Type | Module | Commit Message | Date
| 6c5761f07 | FEAT | INVOICES | feat(invoices): add export dual invoice — Commercial Invoice (USD) + Tax Invoice (INR) | 2026-06-13
| 0eb2ed26e | FEAT | SALES | feat(sales): add driver details warning banner on dispatch order detail page | 2026-06-13
| 03c0113f6 | FEAT | INVOICES | feat(invoices): capture exchange rate date + INR base total for E-Invoice/E-Way Bill | 2026-06-13
| 971880607 | FIX | INVOICES | fix(invoices): set EXPORT_INVOICE type when creating invoice from export dispatch order | 2026-06-13
| 779c19110 | FIX | DISPATCH | fix(dispatch): filter available orders to stock-allocated only | 2026-06-13
| dea33db7e | FIX | HR | fix(hr): target hr.shifts base table for max_headcount column in V8.11 | 2026-06-13
12-Jun-2026 (Friday) — 5 commits (2 feat ¦ 3 fix ¦ 0 other)
| Hash | Type | Module | Commit Message | Date
| 7b0ec19b9 | FEAT | SALES | feat(sales): add GST Supply Sub-Type and export classification to invoices | 2026-06-12
| 7fd391847 | FEAT | SALES | feat(sales): add export order view & edit in dispatch order detail | 2026-06-12
| a04a86135 | FIX | SALES | fix(sales): preserve order_id on draft invoice full update | 2026-06-12
| 28c6f0984 | FIX | SALES | fix(sales): inherit GST sub-type from SO on new invoice creation | 2026-06-12
| 9ec726764 | FIX | SALES | fix(sales): replace hardcoded INR/₹ with dynamic currency across orders and invoices | 2026-06-12
11-Jun-2026 (Thursday) — 8 commits (2 feat ¦ 4 fix ¦ 2 other)
| Hash | Type | Module | Commit Message | Date
| 597758437 | FEAT | DISPATCH | feat(dispatch): add export-order fields to dispatch wizard | 2026-06-11
| 10018605f | FEAT | ORGANIZATION | feat(organization): add LUT/Bond Number to companies and export orders | 2026-06-11
| ca8d0837f | FIX | DISPATCH | fix(dispatch): add CFSG number series and CFS_GODOWN party constraint | 2026-06-11
| 61a667064 | FIX | PARTIES | fix(parties): support international postal code lookup in address dialog | 2026-06-11
| b39b0ed3c | FIX | SALES | fix(sales): show line discount breakdown in Taxes & Charges and Review summary | 2026-06-11
| 8dd50647f | FIX | SALES | fix(sales): show flat discount as ₹/MT in invoice and display in summary | 2026-06-11
| 42159c27d | TEST | E2E | test(e2e): expand functional API test suites for parties, sales, invoices, org | 2026-06-11
| 51ee4b1e3 | OTHER | GENERAL | feat: update | 2026-06-11
10-Jun-2026 (Wednesday) — 21 commits (9 feat ¦ 12 fix ¦ 0 other)
| Hash | Type | Module | Commit Message | Date
| 04fd0fbf3 | FEAT | SALES | feat(sales): use order-level totals in Tax Breakdown card | 2026-06-10
| 842ea7b3e | FEAT | SALES | feat(sales): redesign Tax Breakdown card with rates and Line Total | 2026-06-10
| 359c7c087 | FEAT | SALES | feat(sales): add Discount column to order detail Items tab | 2026-06-10
| 544bf0c43 | FEAT | SALES | feat(sales): show IGST @ X% with rate in line items table footer summary | 2026-06-10
| 328526ea6 | FEAT | SALES | feat(sales): add IGST%/CGST+SGST column to line items table | 2026-06-10
| 8f7850885 | FEAT | SALES | feat(sales): simplify order review table — remove GST col, show pre-GST amount | 2026-06-10
| 6bbd47854 | FEAT | SALES | feat(sales): persist discount_type for flat per-MT discounts on order items | 2026-06-10
| 1bcb1eccd | FEAT | PRICE-CIRCULAR | feat(price-circular): add is_deduction direction to adjustments | 2026-06-10
| dfd6ce9f2 | FEAT | SALES | feat(sales): commission agent currency + fix payment terms overwrite on edit | 2026-06-10
| a4c79605b | FIX | PARTIES | fix(parties): resolve state/country codes to names in edit page addresses | 2026-06-10
| 41fd891ca | FIX | PARTIES | fix(parties): resolve state/country code to name in address display | 2026-06-10
| dc57a0a39 | FIX | SALES | fix(sales): compute taxableBase with charges in Tax Breakdown card | 2026-06-10
| a209bd36d | FIX | SALES | fix(sales): show post-discount subtotal in line items footer | 2026-06-10
| 04054fc4e | FIX | SALES | fix(sales): restore flat discount as per-MT rate (qty × rate = total) | 2026-06-10
| faa3e9a0b | FIX | SALES | fix(sales): flat discount is total fixed amount not per-MT rate | 2026-06-10
| 09e267b19 | FIX | SALES | fix(sales): remove IGST% column from product table, fix colSpan counts | 2026-06-10
| d1ee52417 | FIX | SALES | fix(sales): remove GST% col and show pre-GST amount in line items table | 2026-06-10
| 1374b02c9 | FIX | SALES | fix(sales): backfill discount_type=flat for pre-V7.85 flat discounts | 2026-06-10
| 7f9b6691d | FIX | SALES | fix(sales): show ₹/MT discount when circular uses fixed_per_mt adjustment | 2026-06-10
| 6bfa16610 | FIX | SALES | fix(sales): show base price + discount when circular reduces rate | 2026-06-10
| 2da789175 | FIX | SALES | fix(sales): always show product price when price circular has no matching rule | 2026-06-10
09-Jun-2026 (Tuesday) — 8 commits (5 feat ¦ 1 fix ¦ 2 other)
| Hash | Type | Module | Commit Message | Date
| 089aedc04 | FEAT | SALES | feat(sales): add delivery party/address fields end-to-end | 2026-06-09
| aefa47d6c | FEAT | SALES-ORDERS | feat(sales-orders): show city in address select with full preview | 2026-06-09
| 0b47d97fa | FEAT | SALES-ORDERS | feat(sales-orders): show ship-to address inline below Bill to Customer | 2026-06-09
| 041f9e3c9 | FEAT | SALES-ORDERS | feat(sales-orders): show billing address inline below Bill to Customer | 2026-06-09
| 04c18033b | FEAT | DISPATCH-ORDERS | feat(dispatch-orders): add Pick List print/download to dispatch order detail | 2026-06-09
| 7377f2bc4 | FIX | SALES | fix(sales): auto-populate payment terms from selected customer | 2026-06-09
| 199b84040 | REFACTOR | SALES-ORDERS | refactor(sales-orders): rename Customer Name label to Bill to Customer | 2026-06-09
| e945be97f | REFACTOR | SALES-ORDERS | refactor(sales-orders): remove Bill-to partner override from order form | 2026-06-09
08-Jun-2026 (Monday) — 24 commits (8 feat ¦ 13 fix ¦ 3 other)
| Hash | Type | Module | Commit Message | Date
| 4cc8feb53 | FEAT | PRICE-CIRCULAR | feat(price-circular): auto-apply circular adjustments to invoice line items | 2026-06-08
| b24818071 | FEAT | INVOICES | feat(invoices): add Vessel/Flight Details section for export invoices | 2026-06-08
| 38051470c | FEAT | SALES-ORDERS | feat(sales-orders): redesign section card headers for better UX | 2026-06-08
| bfda01b93 | FEAT | SALES-ORDERS | feat(sales-orders): export enhancements, LC details, commission agent & smart remarks | 2026-06-08
| ffedaf509 | FEAT | INVOICES | feat(invoices): show TCS label as 'TCS (Collection) X%' with rate in all summary views | 2026-06-08
| 5a408345f | FEAT | PRODUCT-CATALOG | feat(product-catalog): auto-select Manufactured when Product Type is Finished Goods | 2026-06-08
| 39c4a13f9 | FEAT | DISPATCH | feat(dispatch): default Freight Terms to Prepaid when order has freight mode/rate | 2026-06-08
| 35aaa8c80 | FEAT | SALES | feat(sales): show full address text below Bill-to / Ship-to dropdowns in order form | 2026-06-08
| 2efcf7990 | FIX | PRICE-CIRCULAR | fix(price-circular): correct range condition matching and form UX | 2026-06-08
| f7d0fe58c | FIX | SALES-ORDERS | fix(sales-orders): remarks presets saving and dropdown visibility | 2026-06-08
| 501c989f7 | FIX | INVOICES | fix(invoices): round TCS amount to higher side using Math.ceil in summary | 2026-06-08
| 466f3049f | FIX | PRODUCT-CATALOG | fix(product-catalog): default isManufactured true on create page for Finished Goods | 2026-06-08
| ce3789a48 | FIX | PRODUCT-CATALOG | fix(product-catalog): default isManufactured to true matching default Finished Goods type | 2026-06-08
| bd982ed62 | FIX | DISPATCH | fix(dispatch): increase width of Vehicle & Route Edit button with px-6 padding | 2026-06-08
| 1b45877a8 | FIX | DISPATCH | fix(dispatch): change Vehicle & Route Edit button to blue fill and larger size | 2026-06-08
| 8e9c72f03 | FIX | DISPATCH | fix(dispatch): change Vehicle & Route Edit button to indigo fill | 2026-06-08
| aca42a540 | FIX | DISPATCH | fix(dispatch): use filled amber background for Vehicle & Route Edit button | 2026-06-08
| 98b059d54 | FIX | DISPATCH | fix(dispatch): highlight Vehicle & Route Edit button with amber colour and bold | 2026-06-08
| 5cc762f14 | FIX | SALES | fix(sales): show 3 decimal places for qty in confirm order ATP dialog | 2026-06-08
| afa4c2bc2 | FIX | SALES | fix(sales): move address preview to right of dropdown in a bordered box | 2026-06-08
| 9fd3cd4fe | FIX | SALES | fix(sales): allow up to 3 decimal places in order line item quantity | 2026-06-08
| 938303ea5 | DOCS | SPECS | docs(specs): update Vessel/Flight Details spec per business review | 2026-06-08
| d244fea8c | DOCS | SALES | docs(sales): update commission & B/L specs per business review | 2026-06-08
| 42fa84795 | OTHER | GENERAL | feat: update | 2026-06-08

## Dhanalakshmi
Weekly Report — Dhanalakshmi ¦ 08-Jun-2026 to 13-Jun-2026
Branch: netique_team_v2 ¦ Sprint 2
MY WEEK IN NUMBERS
| 39 | 8 | 22 | 3 | 10
| Total Commits | New Features | Bug Fixes | Other | Modules
MODULES WORKED ON
| Module | feat | fix | other | Total
| ESS | 3 | 3 | 0 | 6
| GENERAL | 0 | 0 | 6 | 6
| HR | 5 | 10 | 0 | 15
| HR/OVERTIME | 0 | 1 | 0 | 1
| I18N | 0 | 1 | 0 | 1
| LICENSING | 0 | 2 | 0 | 2
| MIGRATIONS | 0 | 0 | 1 | 1
| OVERTIME | 0 | 4 | 0 | 4
| SEEDS | 0 | 0 | 2 | 2
| SEPARATION | 0 | 1 | 0 | 1
13-Jun-2026 (Saturday) — 9 commits (1 feat ¦ 6 fix ¦ 2 other)
| Hash | Type | Module | Commit Message | Date
| e2b7cec27 | FEAT | HR | feat(hr,sales): shift-roster hardening + sales invoice/einvoice enhancements | 2026-06-13
| 6f1cdf460 | FIX | HR | fix(hr): remove duplicate Form import in leave-settlement | 2026-06-13
| 632ece36e | FIX | HR | fix(hr): wrap all separation dialog forms with <Form> provider | 2026-06-13
| 6cf9cac2a | FIX | HR | fix(hr): add Transaction Reference field to FNF payment form | 2026-06-13
| 76ff8f52d | FIX | HR | fix(hr): separation FNF payment + employee termination bugs | 2026-06-13
| 556749913 | FIX | HR | fix(hr): wrap FNF payment dialog form with FormProvider | 2026-06-13
| 017fe6feb | FIX | HR | fix(hr): implement separation document generation endpoints | 2026-06-13
| 35667661a | MERGE | GENERAL | Merge branch 'netique_team_v2' of https://github.com/anandaravi/PapyrusBPApp into netique_ | 2026-06-13
| 6f4309144 | OTHER | GENERAL | chore: untrack generated .d.ts/.d.ts.map files already covered by .gitignore | 2026-06-13
12-Jun-2026 (Friday) — 13 commits (3 feat ¦ 8 fix ¦ 2 other)
| Hash | Type | Module | Commit Message | Date
| bf229d544 | FEAT | HR | feat(hr): comprehensive shift roster hardening — 25 gap closure | 2026-06-12
| da09eaa0f | FEAT | HR | feat(hr): roster weekly_off, DAY_CYCLE pattern, daily view, clear-existing | 2026-06-12
| 62c611cef | FEAT | HR | feat(hr): implement rotating roster support (N-week cycles) | 2026-06-12
| d58835316 | FIX | HR | fix(hr): roster weekly off visibility + remove list/daily tabs | 2026-06-12
| a65066ac6 | FIX | HR | fix(hr): derive is_pf_applicable/is_esi_applicable from pf_number/esi_number | 2026-06-12
| f1340f4b2 | FIX | HR | fix(hr): fix uuid error in generateRoster and relax date inputs | 2026-06-12
| edc044241 | FIX | HR | fix(hr): use String() cast for pg DATE columns in shift-roster service | 2026-06-12
| e6bca0520 | FIX | I18N | fix(i18n): add attendance.reports translation keys for en/hi/ta | 2026-06-12
| a2fd55c1c | FIX | SEPARATION | fix(separation): drop incorrect fk_audit_log_user constraint on separation_audit_log | 2026-06-12
| d2c0f84d9 | FIX | LICENSING | fix(licensing): deduplicate LICENSE_LOCKED toast on login | 2026-06-12
| 536fced74 | FIX | LICENSING | fix(licensing): use req.baseUrl+req.path for allowlist check in stage guard | 2026-06-12
| 33ca8f59a | CHORE | MIGRATIONS | chore(migrations): add V8.08 rotating roster schema support | 2026-06-12
| b53bed0dc | MERGE | GENERAL | Merge branch 'netique_team_v2' of https://github.com/anandaravi/PapyrusBPApp into netique_ | 2026-06-12
11-Jun-2026 (Thursday) — 9 commits (3 feat ¦ 3 fix ¦ 3 other)
| Hash | Type | Module | Commit Message | Date
| 34d6b7a1c | FEAT | ESS | feat(ess): ESS-039–041 carry-forward badge, letter upload, documents | 2026-06-11
| 2126fb793 | FEAT | ESS | feat(ess): i18n — replace all hardcoded strings ESS-030 to ESS-036 | 2026-06-11
| fad8d1549 | FEAT | ESS | feat(ess): close gaps ESS-011 to ESS-019 | 2026-06-11
| 2f61ca472 | FIX | ESS | fix(ess): close RBAC, not-employee, and UX gaps ESS-037 to ESS-044 | 2026-06-11
| ef0647658 | FIX | ESS | fix(ess): close validation gaps ESS-020 to ESS-029 | 2026-06-11
| c8b6c5432 | FIX | ESS | fix(ess): close gaps ESS-001 through ESS-010 — critical bugs + missing actions | 2026-06-11
| faccb707e | CHORE | SEEDS | chore(seeds): add leave types seed for NETIQUE PAPER MILL | 2026-06-11
| 8cdf976ea | CHORE | SEEDS | chore(seeds): link test user to EMP-00001 for ESS dev testing | 2026-06-11
| ab2fd67f7 | MERGE | GENERAL | Merge branch 'netique_team_v2' of https://github.com/anandaravi/PapyrusBPApp into netique_ | 2026-06-11
10-Jun-2026 (Wednesday) — 3 commits (1 feat ¦ 1 fix ¦ 1 other)
| Hash | Type | Module | Commit Message | Date
| bf3898b84 | FEAT | HR | feat(hr): complete overtime module — gaps #43-61 end-to-end | 2026-06-10
| 6848b7fc6 | FIX | OVERTIME | fix(overtime): i18n reports CSV headers + locale-aware month picker | 2026-06-10
| 2a5ab88c8 | MERGE | GENERAL | Merge branch 'netique_team_v2' of https://github.com/anandaravi/PapyrusBPApp into netique_ | 2026-06-10
09-Jun-2026 (Tuesday) — 5 commits (0 feat ¦ 4 fix ¦ 1 other)
| Hash | Type | Module | Commit Message | Date
| 6f9403eef | FIX | OVERTIME | fix(overtime): replace hardcoded data with DB-backed sources (#70-71) | 2026-06-09
| 5eb99225d | FIX | OVERTIME | fix(overtime): UX/design gap closure (#72-80) | 2026-06-09
| cd9be592c | FIX | OVERTIME | fix(overtime): resolve type/API contract mismatches (#66-69) | 2026-06-09
| dfb66afd2 | FIX | HR/OVERTIME | fix(hr/overtime): close 15 validation, feature, and UX gaps | 2026-06-09
| 6114a5769 | MERGE | GENERAL | Merge branch 'netique_team_v2' of https://github.com/anandaravi/PapyrusBPApp into netique_ | 2026-06-09

## Issues This Week
Issues Fixed This Week ¦ 08-Jun-2026 to 13-Jun-2026
72 issues logged this week across Thiravidam, Gowtham, Dhanalakshmi
| ID | Owner | Reported By | Description | Severity | Status | Resolution
Thiravidam — 20 issues ¦ ✅ 20 Fixed ¦ ⚠ 0 Open
| #1 | Thiravidam | Manjunath | Procurement > Supplier Quotations > List — Quotation list shows wrong total amount (SQ-2606-0006: ₹1 | medium | Completed | Fixed: Added header total recalculation (subtotal, tax_amount, total_amount) aft
| #2 | Thiravidam | Manjunath | Procurement > Supplier Quotations > List — Import quotation (SQ-2606-0002) showing foreign currency | high | Completed | Fixed: List page now renders landedCostInr for IMPORT supplier type instead of t
| #3 | Thiravidam | Manjunath | Procurement > Purchase Requisitions — Line item Net Total shows tax-inclusive value (₹1,050) in line | medium | Completed | Fixed: Backend calculateLineAmounts uses netAmt (post-discount+tax) for estimate
| #4 | Thiravidam | Thiravidam | Procurement > Purchase Orders > List — Total Amount column showing ₹0 for all POs. | medium | Completed | Fixed: PO list column accessor changed from netAmount (non-existent) to totalAmo
| #5 | Thiravidam | Manjunath | Procurement > Purchase Orders — Converting quotation to PO results in tax showing zero in PO view an | high | Completed | Fixed: Line mapper corrected api.tax_rate → api.igst_percent; header mapper corr
| #6 | Thiravidam | Manjunath | Master Data > Supplier Master > Certifications — 500 Internal Server Error when saving certification | high | Completed | Fixed: Aligned all three layers — DB constraint codes (ISO_9001, ISO_14001, etc.
| #7 | Thiravidam | Manjunath | Production > Material Requisitions — After clicking Post Goods Issue, Lines tab shows Issued = 0 for | high | Completed | Fixed: issue() now checks for pending WO materials first; if already issued via
| #8 | Thiravidam | Manjunath | Production > Material Requisitions — Issuing material via Work Order material dialog does not update | medium | Completed | Fixed: workOrderService.issueMaterial() and postGoodsIssue() now sync wo_materia
| #9 | Thiravidam | Thiravidam | Inventory > Material Requests > Lines tab — Lines tab shows quantity_issued = 0 even when material i | high | Completed | Fixed in material-issue.service.ts: sync MR lines on approveIssue (final level),
| #10 | Thiravidam | Thiravidam | Master Data > Business Partners — Address display and edit page showing raw state/country codes (e.g | medium | Completed | Commits: 41fd891ca, a4c79605b
| #11 | Thiravidam | Thiravidam | Procurement > Supplier Quotations > List — Total amount shown without discount. Per-line discount_am | high | Completed | Fixed createQuotation and updateQuotation in supplier-quotation.service.ts to ac
| #12 | Thiravidam | Thiravidam | Procurement > Supplier Quotations > List — Import quotation landed cost showing wrong value. clearin | medium | Completed | Migration V7.98 recalculates line and header landed_cost_inr using cf×qty + lt×q
| #13 | Thiravidam | Thiravidam | Inventory > Material Requests > Lines tab — quantity_issued showed 0 even when material issues were | high | Completed | Fixed material-issue.service.ts: applyIssuance on approveIssue (final level), de
| #14 | Thiravidam | Ram Vicky | Procurement > Supplier Quotations > Comparison — Quotation comparison page had broken visibility in | medium | Fixed | Fixed: Added dark: variants for all hardcoded light-mode backgrounds in comparat
| #28 | Thiravidam | Ragesh | Sales > Sales Orders > Create Form > Bill to Customer — Customer dropdown only showed party name wit | low | Fixed | Fixed: fetchCustomers now maps partyCode → code. SelectItem renders as "code - n
| #29 | Thiravidam | Ragesh | Sales > Sales Orders > Line Items > Product Search — Newly created products not appearing immediatel | medium | Fixed | Fixed: Added 30s stale TTL to browse list cache (browseFetchedAtRef) — re-fetche
| #32 | Thiravidam | Ragesh | Sales > Sales Orders > Line Items > Product Search — Product search was showing all product types (r | medium | Fixed | Fixed: Added productType="finished_goods" to both ProductAutocomplete instances
| #33 | Thiravidam | Ragesh | Sales > Sales Orders > Bill to Customer — Standard order type was showing only DOMESTIC-typed custom | medium | Fixed | Fixed: fetchCustomers now fetches all customers for non-export orders and filter
| #34 | Thiravidam | Ragesh | Sales > Sales Orders > Round Off — Round off toggle was disabled by default on new sales orders, req | low | Fixed | Fixed: Changed roundOff default value from false to true in OrderCreateEditPage.
| #72 | Thiravidam | Ragesh | Sales > Sales Orders > List > Print — Print Report button was printing the entire order list as one | low | Fixed
Gowtham — 5 issues ¦ ✅ 1 Fixed ¦ ⚠ 4 Open
| #30 | Gowtham | Manjunath | Sales & Distribution | medium | Fixed | give an waring message like please enter driver details to enable start loading
| #31 | Gowtham | Kalatheeswaran | Sales & Distribution >invoicing >sales invoices> Generate from so -In sales invoices ,generate from | high | Unfixed
| #35 | Gowtham | Kalatheeswaran | Sales & Distribution >invoicing >sales invoices> create invoice -In sales invoices ,creating new inv | high | Unfixed
| #58 | Gowtham | Kalatheeswaran | Sales & Distribution >invoicing >sales invoicing > more option menu -In sales invoices ,after you cl | medium | Unfixed
| #73 | Gowtham | Kalatheeswaran | sales & Distribution >invoicing >sales invoicing > more option menu -In sales invoices ,after you cl | medium | Unfixed
Dhanalakshmi — 47 issues ¦ ✅ 35 Fixed ¦ ⚠ 12 Open
| #15 | Dhanalakshmi | Dhanalakshmi | Shift Roster>Issue: MONTHLY and CUSTOM patterns do nothing special Where: generateRoster Detail: B | medium | Fixed
| #16 | Dhanalakshmi | Dhanalakshmi | Error messages embed raw UUIDs, not employee codes-Every error entry says "abc-123-uuid on 2026-06-1 | medium | Fixed
| #17 | Dhanalakshmi | Dhanalakshmi | For each employee × each date × shift: 4 sequential DB queries (existing check, leave check, holi | medium | Fixed
| #18 | Dhanalakshmi | Dhanalakshmi | Holiday query does company_id = $2 OR company_id IS NULL but ignores plant_id-scoped | medium | Fixed
| #19 | Dhanalakshmi | Dhanalakshmi | holidays. An employee in Plant B will have Plant A's holidays applied (or vice-versa). | medium | Fixed
| #20 | Dhanalakshmi | Dhanalakshmi | Query does start_date >= $2 AND start_date <= $3, so a permanent assignment | medium | Fixed
| #21 | Dhanalakshmi | Dhanalakshmi | (start=2026-01-01, end=NULL) is invisible when querying 2026-06-01 to 2026-06-30 unless its | medium | Fixed
| #22 | Dhanalakshmi | Dhanalakshmi | start_date falls in that range. Should use overlap: start_date <= $3 AND (end_date IS NULL OR | medium | Fixed
| #23 | Dhanalakshmi | Dhanalakshmi | end_date >= $2). | medium | Fixed
| #24 | Dhanalakshmi | Dhanalakshmi | The in-memory weeklyAssigned map only tracks assignments created during this run. If an employee | medium | Fixed
| #25 | Dhanalakshmi | Dhanalakshmi | DAY_CYCLE skips check for empOffDays — actually it does check, but dayCycleShiftForDate still | medium | Fixed
| #26 | Dhanalakshmi | Dhanalakshmi | Delete template doesn't check for active generated assignments.deleteRosterTemplate Detail: Hard-de | medium | Fixed
| #27 | Dhanalakshmi | Dhanalakshmi | available_capacity returns minimum_staffing, not maximum.now reads minimum_staffing from production. | medium | Fixed
| #36 | Dhanalakshmi | Dhanalakshmi | Roster generation does not enforce Factories Act §54 daily 9-hour cap — shifts exceeding 9 hrs are | medium | Fixed
| #37 | Dhanalakshmi | Dhanalakshmi | Roster generation does not enforce Factories Act §55 mandatory 30-min break for shifts >5 hours — b | medium | Fixed
| #38 | Dhanalakshmi | Dhanalakshmi | No spread-of-hours check (Factories Act §56 max 10.5 hrs) — shift start-to-end span is unbounded | medium | Fixed
| #39 | Dhanalakshmi | Dhanalakshmi | min_rest_hours_between_shifts defaults to 0 instead of statutory 11 hrs — shift rotations can be b | medium | Fixed
| #40 | Dhanalakshmi | Dhanalakshmi | Roster generator enforces max_headcount upper bound but never blocks assignments below minimum_sta | medium | Fixed
| #41 | Dhanalakshmi | Dhanalakshmi | No consecutive night shift cap — employees can be assigned unlimited sequential night shifts with n | medium | Fixed
| #42 | Dhanalakshmi | Dhanalakshmi | Quarterly overtime quota (Factories Act §64 max 75 hrs/quarter) not tracked or enforced at assignm | medium | Fixed
| #43 | Dhanalakshmi | Dhanalakshmi | Blocking §51 day-7 assignment logs an error but does not create a compensatory rest day entitlemen | medium | Fixed
| #44 | Dhanalakshmi | Dhanalakshmi | Shift validator accepts identical start_time and end_time — zero-duration shifts are not rejected | medium | Fixed
| #45 | Dhanalakshmi | Dhanalakshmi | Shift validator does not reject crosses_midnight=false when end_time < start_time — negative-durat | medium | Fixed
| #46 | Dhanalakshmi | Dhanalakshmi | break_duration_minutes is not compared to shift duration — a break longer than the shift itself is | medium | Fixed
| #47 | Dhanalakshmi | Dhanalakshmi | night_shift_premium_percentage is accepted on any shift regardless of whether start_time falls in | medium | Fixed
| #48 | Dhanalakshmi | Dhanalakshmi | No separate minimum_staffing floor for night shifts — Indian safety codes require a higher mandato | medium | Fixed
| #49 | Dhanalakshmi | Dhanalakshmi | Shift assigned on weekly-off day renders orange warning in matrix but is not blocked and saves wit | medium | Fixed
| #50 | Dhanalakshmi | Dhanalakshmi | Shift assigned on public holiday renders red warning in matrix but saves without blocking, compens | medium | Fixed
| #51 | Dhanalakshmi | Dhanalakshmi | getRosterAvailability returns is_understaffed flag but the matrix table never renders it — manager | medium | Fixed
| #52 | Dhanalakshmi | Dhanalakshmi | MAX_MATRIX_DAYS = 30 truncates 31-day months — the last day of July, August, October, December, an | medium | Fixed
| #53 | Dhanalakshmi | Dhanalakshmi | Manual assign dialog has no past-date guard — shift assignments can be backdated freely (CSV impor | medium | Fixed
| #54 | Dhanalakshmi | Dhanalakshmi | Roster matrix has no plant filter — multi-plant factories cannot view or generate a single plant's | medium | Fixed
| #55 | Dhanalakshmi | Dhanalakshmi | ROTATING template generation does not validate that all configured cycle groups contain at least on | medium | Fixed
| #56 | Dhanalakshmi | Dhanalakshmi | DAY_CYCLE block daysCount values are not summed and validated against the intended cycle period — | medium | Fixed
| #57 | Dhanalakshmi | Dhanalakshmi | GenerateRosterSchema has no maximum date-range guard — a multi-year generation range is accepted, | medium | Fixed
| #59 | Dhanalakshmi | Dhanalakshmi | Break times not validated against shift window shiftBreakSchema accepts any start_time/end_time wit | medium | Open
| #60 | Dhanalakshmi | Dhanalakshmi | Multiple breaks not checked for mutual overlap When breaks array has more than one entry, no valida | medium | Open
| #61 | Dhanalakshmi | Dhanalakshmi | Factories Act §54 daily 9-hour cap not in shift validator shiftCrossFieldCheck enforces the 4-hour | medium | Open
| #62 | Dhanalakshmi | Dhanalakshmi | Factories Act §55 mandatory 30-min break not enforced in validator Shift duration > 5 hours is acce | medium | Open
| #63 | Dhanalakshmi | Dhanalakshmi | Factories Act §56 spread-of-hours ceiling (10.5 h) not checked No validation that end_time − start_ | medium | Open
| #64 | Dhanalakshmi | Dhanalakshmi | grace_period_minutes and overtime_threshold_minutes not bounded by shift duration Both fields can e | medium | Open
| #65 | Dhanalakshmi | Dhanalakshmi | Employment type vs assignment type mismatch deferred but never implemented shift-assignment.validat | medium | Open
| #66 | Dhanalakshmi | Dhanalakshmi | Shift change request does not verify employee is assigned to from_shift_id on change_date CreateS | medium | Open
| #67 | Dhanalakshmi | Dhanalakshmi | Shift swap request does not verify both employees have shifts to swap RequestShiftSwapSchema valida | medium | Open
| #68 | Dhanalakshmi | Dhanalakshmi | WFH request not blocked for night shift workers in manufacturing CreateWFHRequestSchema imposes no | medium | Open
| #69 | Dhanalakshmi | Dhanalakshmi | STATE holiday type accepted without plant_id CreateHolidaySchema makes plant_id optional for all ho | medium | Open
| #70 | Dhanalakshmi | Dhanalakshmi | Comp-off credit insert (GAP-08) has no guard for missing 'CO' leave type generateRoster inserts int | medium | Open

## Daily Activity
Daily Commit Activity ¦ 08-Jun-2026 to 13-Jun-2026
| Developer | Mon 08 | Tue 09 | Wed 10 | Thu 11 | Fri 12 | Sat 13 | Total
| Thiravidam | 10 | 2 | 2 | 20 | 16 | 7 | 57
| Gowtham | 24 | 8 | 21 | 8 | 5 | 6 | 72
| Dhanalakshmi |  | 5 | 3 | 9 | 13 | 9 | 39
| TOTAL | 34 | 15 | 26 | 37 | 34 | 22 | 168
Colour scale: grey=0 light blue=1-3 medium blue=4-8 dark blue=9-15 deep blue=16+